## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
Land Acquisition App
* = an automatically calculated cell
| TASK NAME |  | START DATE | Day of Project | Days of Work | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
| Bokeh App Framework |  | 2019-07-02 | 0 | 7 | 2019-07-09 | 8 | 6.65 | 1.35 |  | 95%
| Implement Excel Upload/Download |  | 2019-07-02 | 0 | 6 | 2019-07-08 | 7 | 4.8 | 2.2 |  | 80%
| Create Database Schema |  | 2019-07-03 | 1 | 7 | 2019-07-10 | 8 | 6.65 | 1.35 |  | 95%
| Embed in Flask or Django | Flask integration complete | 2019-07-08 | 6 | 6 | 2019-07-14 | 7 | 5.7 | 1.3 |  | 95%
| Dockerize | Using Docker Toolbox need to access http://192.168.99.100:5000. Pandas/Numpy must be compiled in C, Could not find pre-built images on the hub, Bokeh may require wheel installs and C compilation | 2019-07-14 | 12 | 5 | 2019-07-19 | 6 | 0.75 | 5.25 |  | 15%
| Map |  | 2019-07-07 | 5 | 7 | 2019-07-14 | 8 | 1.75 | 6.25 |  | 25%
| Scatterplot |  | 2019-07-05 | 3 | 9 | 2019-07-14 | 10 | 7.65 | 2.35 |  | 85%
| Comps |  | 2019-07-04 | 2 | 7 | 2019-07-11 | 8 | 3.15 | 4.85 |  | 45%
| Absorption |  | 2019-07-04 | 2 | 9 | 2019-07-13 | 10 | 1.35 | 8.65 |  | 15%
| Stacked Vbar |  | 2019-07-05 | 3 | 9 | 2019-07-14 | 10 | 1.35 | 8.65 |  | 15%
| Table |  | 2019-07-05 | 3 | 7 | 2019-07-12 | 8 | 6.3 | 1.7 |  | 90%
| Color Scheme |  | 2019-07-05 | 3 | 6 | 2019-07-11 | 7 | 0.9 | 6.1 |  | 15%
| Layouts |  | 2019-07-14 | 12 | 6 | 2019-07-20 | 7 | 0 | 7 |  | 0%
| Meta Functions & Interconnectivity |  | 2019-07-16 | 14 | 6 | 2019-07-22 | 7 | 0.3 | 6.7 |  | 5%
| Text/Instructions |  | 2019-07-18 | 16 | 6 | 2019-07-24 | 7 | 0 | 7 |  | 0%
| Plot Tools |  | 2019-07-14 | 12 | 14 | 2019-07-28 | 15 | 2.1 | 12.9 |  | 15%
| User Sign In |  | 2019-07-15 | 13 | 17 | 2019-08-01 | 18 | 0 | 18 |  | 0%
Formulas:
END DATE = +[Days of Work]+[START DATE]
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])